## Slide 1: State Action Plan Andhra Pradesh

## Slide 2
Goal | Description | Status (Current Arrangements) | Timeline (Target Month)
Onboarding onto UNNATI |  |  | 
Exhaustive list of TIs in the State/UT | Prepare the exhaustive list of TIs in the State/UT for onboarding on UNNATI. | No | 30/10/2026
Onboarding on UNNATI | Complete/saturate TI profiles on UNNATI with basic details, available infrastructure, faculty and training courses offered. | No | 30/10/2026
Analyse CBP-based demand through UNNATI and Publish Calendar | Each TI analyses aggregate demand to create CBP aligned training calendars. | On Going | 30/11/2026
Updated Courseware | Each TI creates CBP aligned/updates courseware, or borrows through UNNATI exchange where required. | Yes | 30/12/2026
Andhra Pradesh
UNNATI: Step-Level Actions and Timelines

## Slide 3: Andhra Pradesh
Training Institutes invest significantly in course design, delivery, and learner engagement. However, completion, participation and satisfaction do not necessarily demonstrate that the intended learning outcomes have been achieved. |  | 
What quality measures and evidence do Training Institutes currently use across the learning lifecycle to ensure that: |  | 
S. No. | Description | Remarks
1 | Curriculum design and learning experiences are aligned to the expected competencies and learning outcomes; | The use of AI- Enabled Capacity Building Plan shall support Andhra Pradesh in developing courses aligned to expected competencies. The competency aligned and AI enabled learning experiences will facilitate expected Training Outcomes- For the state, department, and citizens.
2 | Learning is relatable & applicable to the learners. How are these evidences used to monitor, improve and redesign the curriculum? | The trainings shall be relevant for the trainees whenever and where ever they need. Their experiences can be used to simulate, gamify, and personalise learnings for the learners, and help them in solving their day to day problems.
For reference you can use the following documents from the folder made available to you:
Karmayogi Quality Framework
National Curriculum Design Framework
UNNATI: Step-Level Actions and Timelines

## Slide 4
Andhra Pradesh
Governance: Step-Level Actions and Timelines (1/2)
Goal | Description | Status (Current Arrangements) | Timeline (Target Month)
Establishing State Governance Structure |  |  | 
Approve operationalisation of the TI Transformation Framework | State/UT approves operationalisation of the TI Transformation Framework. | No | December, 2026
Constitute the Steering Committee | State/UT constitutes and notifies the State Capacity Building Steering Committee. | Constituted | 
Notify the nodal TI | State/UT notifies the nodal TI and its Terms of Reference. | Under Discussion | November, 2026
Finalise recruitment process for Nodal TI Head | State/UT finalises the recruitment process for appointment of Head of Nodal TI. | Under Discussion | December, 2026

## Slide 5
Goal | Description | Status (Current Arrangements) | Timeline (Target Month)
Delegation and Staffing |  |  | 
Delegate tiered autonomy | Appropriate administrative autonomy granted to TIs basis pre-defined criteria. | Partial Autonomy is already at the TI level, New Avenues shall be explored | March, 2027
Appoint leadership | State begins the search and selection process for ATI Head, based on finalised recruitment process. | Under Process | 1st December, 2026
Constitute the committees | TI constitutes its operational-level committees Governing Body Academic Council Programme Advisory Collaboration Committee Frontier Technologies | Tis have one or other such committees, those lacking will be supported eventually | January, 2027
Andhra Pradesh
Governance: Step-Level Actions and Timelines (2/2)

## Slide 6
Goal | Description | Status (Current Arrangements) | Timeline (Target Month)
AI Governance |  |  | 
Finalise AI adoption guidelines | State/UT finalises AI adoption guidelines for the TI ecosystem, covering AI roles, data curation, guardrails and use cases. | Yes | January, 2027
Procure and deploy AI tools | TIs procure and deploy approved AI tools as per State/UT AI guidelines and stated safeguards. | Under Discussion | March, 2027
Andhra Pradesh
Digital & AI: Step-Level Actions and Timelines (1/2)

## Slide 7
Goal | Description | Status (Current Arrangements) | Timeline (Target Month)
Capability and Delivery |  |  | 
Build faculty AI capability | TI trains faculty and staff to use authorised AI tools for courseware creation, validation and delivery support. | Yes | December, 2026
Integrate AI-supported delivery | Use approved AI tools for curriculum support, simulations, learner assistance and continuous improvement, with human oversight. | NO | January, 2027
Andhra Pradesh
Digital & AI: Step-Level Actions and Timelines (2/2)