## Slide 1: State Action Plan Puducherry

## Slide 2
Goal | Description | Status (Current Arrangements) | Timeline (Target Month)
Onboarding onto UNNATI |  |  | 
Exhaustive list of TIs in the State/UT | Prepare the exhaustive list of TIs in the State/UT for onboarding on UNNATI. | We have one ATI which will be onbaorded | 1 month
Onboarding on UNNATI | Complete/saturate TI profiles on UNNATI with basic details, available infrastructure, faculty and training courses offered. | Will be completed | 6 months
Analyse CBP-based demand through UNNATI and Publish Calendar | Each TI analyses aggregate demand to create CBP aligned training calendars. |  | 
Updated Courseware | Each TI creates CBP aligned/updates courseware, or borrows through UNNATI exchange where required. |  | 
Puducherry
UNNATI: Step-Level Actions and Timelines

## Slide 3: Puducherry
Training Institutes invest significantly in course design, delivery, and learner engagement. However, completion, participation and satisfaction do not necessarily demonstrate that the intended learning outcomes have been achieved. |  | 
What quality measures and evidence do Training Institutes currently use across the learning lifecycle to ensure that: |  | 
S. No. | Description | Remarks
1 | Curriculum design and learning experiences are aligned to the expected competencies and learning outcomes; | Puducherry ATI intends to review training needs, course objectives, session plans, resource persons’ material and assessments before delivery. The training calendar, approved course outlines, competency, role mapping, session plans and assessment results will be aligned to the expected outcomes.
2 | Learning is relatable & applicable to the learners. How are these evidences used to monitor, improve and redesign the curriculum? | ATI would use practical examples, case discussions and exercises relevant to participants’ duties. Participant feedback, assessment results, and course completion records would help identify the content that needs revision.
For reference you can use the following documents from the folder made available to you:
Karmayogi Quality Framework
National Curriculum Design Framework
UNNATI: Step-Level Actions and Timelines

## Slide 4: UNNATI Section: Additional Remarks
Use this slide for additional remarks, contextual constraints or relevant information from the UNNATI section.
Remarks:
ATI, Puducherry has not yet been onboarded onto UNNATI.
Request to onboard so as to conduct various training programmes

## Slide 5
Puducherry
Governance: Step-Level Actions and Timelines (1/2)
Goal | Description |  | Status (Current Arrangements) | Timeline (Target Month)
Establishing State Governance Structure |  |  |  | 
Approve operationalisation of the TI Transformation Framework | State/UT approves operationalisation of the TI Transformation Framework. | State/UT approves operationalisation of the TI Transformation Framework. | Since we are a new ATI, the TI transformation network will be initiated | 3 months
Constitute the Steering Committee | State/UT constitutes and notifies the State Capacity Building Steering Committee. | State/UT constitutes and notifies the State Capacity Building Steering Committee. | Will be notified | 
Notify the nodal TI | State/UT notifies the nodal TI and its Terms of Reference. | State/UT notifies the nodal TI and its Terms of Reference. |  | 
Finalise recruitment process for Nodal TI Head | State/UT finalises the recruitment process for appointment of Head of Nodal TI. | State/UT finalises the recruitment process for appointment of Head of Nodal TI. | Will be finalised | 6 months

## Slide 6
Goal | Description |  | Status (Current Arrangements) | Timeline (Target Month)
Delegation and Staffing |  |  |  | 
Delegate tiered autonomy | Appropriate administrative autonomy granted to TIs basis pre-defined criteria. | Defined in the G.O. Ms. No. 04 / A2 / ARW /2025, Puducherry, dated 19th June 2025 |  | 
Appoint leadership | State begins the search and selection process for ATI Head, based on finalised recruitment process. | The Chief Secretary to Government is the Director-General (Training) The Secretary, Administrative Reforms Wing is the Head and Additional Director General (Administration) of the Administrative Training Institute of Puducherry. ATI Head selection process will be finalised | Chief Secretary to Government shall be the Director-General (Training) and Secretary, Administrative Reforms Wing shall be the Head and Additional Director General (Administration) of the Administrative Training Institute of Puducherry. | 6 months
Constitute the committees | TI constitutes its operational-level committees Governing Body Academic Council Programme Advisory Collaboration Committee Frontier Technologies | Governing body and Executive Committee constituted vide G.O. Ms. No. 04 / A2 / ARW /2025, Puducherry, dated 19th June 2025 Other committees will be constituted | Constitutted vide G.O. Ms. No. 04 / A2 / ARW /2025, Puducherry, dated 19th June 2025 | 
Puducherry
Governance: Step-Level Actions and Timelines (2/2)

## Slide 7: Governance: Additional Remarks
Use this slide for additional remarks, contextual constraints or relevant information from the Governance section.
Remarks:
The Administrative Training Institute (ATI), Puducherry, has been constituted recently
Would benefit from structured mentoring and technical support to develop into a fully functional capacity-building institution.
Challenges in identifying a sufficiently broad pool of qualified resource persons and trainers across specialised subjects.
Support from the Capacity Building Commission in trainer development, access to empanelled experts, and collaboration with established ATIs would help address these gaps.

## Slide 8
Goal | Description | Status (Current Arrangements) | Timeline (Target Month)
AI Governance |  |  | 
Finalise AI adoption guidelines | State/UT finalises AI adoption guidelines for the TI ecosystem, covering AI roles, data curation, guardrails and use cases. | AI adoption process will be initiated and will be completed at the earliest | 12 months
Procure and deploy AI tools | TIs procure and deploy approved AI tools as per State/UT AI guidelines and stated safeguards. |  | 
Puducherry
Digital & AI: Step-Level Actions and Timelines (1/2)

## Slide 9
Goal | Description | Status (Current Arrangements) | Timeline (Target Month)
Capability and Delivery |  |  | 
Build faculty AI capability | TI trains faculty and staff to use authorised AI tools for courseware creation, validation and delivery support. | AI adoption process will be initiated | 12 months
Integrate AI-supported delivery | Use approved AI tools for curriculum support, simulations, learner assistance and continuous improvement, with human oversight. |  | 
Puducherry
Digital & AI: Step-Level Actions and Timelines (2/2)

## Slide 10: Digital & AI Section: Additional Remarks from TIs
Use this slide for additional remarks, contextual constraints or relevant information from the Digital & AI section.
Remarks:
Puducherry ATI seeks guidance from the Capacity Building Commission on suitable AI use cases, data safeguards and preparation of guidelines appropriate for a newly constituted ATI.
Procurement, faculty training and AI-supported delivery will be taken up in stages after the guidelines and authorised tools are finalised.