## Slide 1: State Action Plan Telangana

## Slide 2
Goal | Description | Status (Current Arrangements) | Timeline (Target Month)
Onboarding onto UNNATI |  |  | 
Exhaustive list of TIs in the State/UT | Prepare the exhaustive list of TIs in the State/UT for onboarding on UNNATI. | No | 31/12/2026
Onboarding on UNNATI | Complete/saturate TI profiles on UNNATI with basic details, available infrastructure, faculty and training courses offered. | No | 31/12/2026
Analyse CBP-based demand through UNNATI and Publish Calendar | Each TI analyses aggregate demand to create CBP aligned training calendars. | Yes | 31/3/2027
Updated Courseware | Each TI creates CBP aligned/updates courseware, or borrows through UNNATI exchange where required. | Yes | 31/3/2027
Telangana
UNNATI: Step-Level Actions and Timelines

## Slide 3: Telangana
Training Institutes invest significantly in course design, delivery, and learner engagement. However, completion, participation and satisfaction do not necessarily demonstrate that the intended learning outcomes have been achieved. |  | 
What quality measures and evidence do Training Institutes currently use across the learning lifecycle to ensure that: |  | 
S. No. | Description | Remarks
1 | Curriculum design and learning experiences are aligned to the expected competencies and learning outcomes; | Course design is mapped to CBP/KQF competencies and the National Curriculum Design Framework; content is vetted by subject experts and the Academic Council. Pre- and post-training assessments track outcome alignment. Formal quality checklist to be institutionalised by 31/3/2027.
2 | Learning is relatable & applicable to the learners. How are these evidences used to monitor, improve and redesign the curriculum? | Post-training feedback, learner assessments and on-the-job application follow-ups are collected and reviewed periodically by the Academic Council to refine and redesign curricula. Structured impact tracking (Kirkpatrick Levels 1-4) targeted by 31/3/2027.
For reference you can use the following documents from the folder made available to you:
Karmayogi Quality Framework
National Curriculum Design Framework
UNNATI: Step-Level Actions and Timelines

## Slide 4: UNNATI Section: Additional Remarks
Use this slide for additional remarks, contextual constraints or relevant information from the UNNATI section.
Remarks:
TI list and profile onboarding on UNNATI to be completed by 31/12/2026, followed by CBP-aligned training calendars and updated courseware by 31/3/2027. Key dependencies: data submission by all TIs, nodal TI coordination, and courseware exchange through UNNATI.

## Slide 5
Telangana
Governance: Step-Level Actions and Timelines (1/2)
Goal | Description | Status (Current Arrangements) | Timeline (Target Month)
Establishing State Governance Structure |  |  | 
Approve operationalisation of the TI Transformation Framework | State/UT approves operationalisation of the TI Transformation Framework. | No | 31/12/2026
Constitute the Steering Committee | State/UT constitutes and notifies the State Capacity Building Steering Committee. | In progress | 31/12/2026
Notify the nodal TI | State/UT notifies the nodal TI and its Terms of Reference. | In progress | 31/12/2026
Finalise recruitment process for Nodal TI Head | State/UT finalises the recruitment process for appointment of Head of Nodal TI. | No | 31/12/2026

## Slide 6
Goal | Description | Status (Current Arrangements) | Timeline (Target Month)
Delegation and Staffing |  |  | 
Delegate tiered autonomy | Appropriate administrative autonomy granted to TIs basis pre-defined criteria. | No | 31/3/2027
Appoint leadership | State begins the search and selection process for ATI Head, based on finalised recruitment process. | No | 31/3/2027
Constitute the committees | TI constitutes its operational-level committees Governing Body Academic Council Programme Advisory Collaboration Committee Frontier Technologies | No | 31/12/2026
Telangana
Governance: Step-Level Actions and Timelines (2/2)

## Slide 7: Governance: Additional Remarks
Use this slide for additional remarks, contextual constraints or relevant information from the Governance section.
Remarks:
Steering Committee and nodal TI notification are in progress and targeted for 31/12/2026, along with TI-level committees. Framework approval, recruitment process for the Nodal TI Head, tiered autonomy and leadership selection follow by 31/3/2027, subject to State approvals.

## Slide 8
Goal | Description | Status (Current Arrangements) | Timeline (Target Month)
AI Governance |  |  | 
Finalise AI adoption guidelines | State/UT finalises AI adoption guidelines for the TI ecosystem, covering AI roles, data curation, guardrails and use cases. | No | 31/12/2026
Procure and deploy AI tools | TIs procure and deploy approved AI tools as per State/UT AI guidelines and stated safeguards. | No | 31/3/2027
Telangana
Digital & AI: Step-Level Actions and Timelines (1/2)

## Slide 9
Goal | Description | Status (Current Arrangements) | Timeline (Target Month)
Capability and Delivery |  |  | 
Build faculty AI capability | TI trains faculty and staff to use authorised AI tools for courseware creation, validation and delivery support. | Yes | 31/3/2027
Integrate AI-supported delivery | Use approved AI tools for curriculum support, simulations, learner assistance and continuous improvement, with human oversight. | Yes i) Using AI for internal working | 31/3/2027
Telangana
Digital & AI: Step-Level Actions and Timelines (2/2)

## Slide 10: Digital & AI Section: Additional Remarks from TIs
Use this slide for additional remarks, contextual constraints or relevant information from the Digital & AI section.
ChatGPT, Claude, Gemini are being used for internal AI-assisted work.
Remarks: